## NIST Framework
Hospital - Information Security Risk-Aligned Framework | [9 empty] | Maturity Roadmap FY2015 | [6 empty] | Action Plan FY2015 | [5 empty] | Action Plan FY2016 |  |  |  | Action Plan FY2017
Function | Category Unique Identifier | Category | InfoSec Service Catalog | Risk Rank | SANS Top Twenty | FY2015 $ | FY2016 $ | FY2017 $ | NIST Policy Family | 0 Basic | 1 Controlled | 2 Standards | 3 Rational | 4 Virtual | 5 Service | 6 Dynamic | FY2014-Q3 | FY2014-Q4 | FY2015-Q1 | FY2015-Q2 | FY2015-Q3 | FY2015-Q4 | FY2016-Q1 | FY2016-Q2 | FY2016-Q3 | FY2016-Q4 | FY2017-Q1 | FY2017-Q2 | FY2017-Q3 | FY201-Q4
Identify | AM | Asset Management | Operations Security - Asset Management - Physical and Environmental | 4 7 |  | $xxx $xx |  |  | DI DM | [8 empty] | MDM |  | Asset Strategy |  |  | Review |  |  |  | Project 7A
| BE | Business Environment | Governance - Regulatory, Legal, Compliance | All |  |  |  |  | AP |  |  |  |  | Metrics |  |  | PCI, HIPAA |  | Risk Program |  |  |  | Risk Program Review
| GV | Governance | Governance - Security Information Management | 5 |  | $xxx |  |  | AU PL PM | [7 empty] | Gov. Model |  |  | Policy Dev. | Policy Dev. | Policy Review |  |  |  | Policy Review |  |  |  | Policy Review
| RA | Risk Assessment | Security and Risk Assessments | 5a |  |  |  |  | AR | [7 empty] | RA Prog. | Upgrade |  | Automate | Dashboard
| RM | Risk Management | Governance - Risk Management | 5b |  |  |  |  | AR | [7 empty] | Framework | Review | Alignment | Integration 1 |  | Integration 2 |  | Integration 3 |  | Integration 4 |  | Review
Protect | AC | Access Control | Identity and Access Management (IAM) - IAM - SSO - NAC - RBAC | 2 3 6 9 |  | $xxx $xx $xx $xxx | $xxx | $xxx | AC IA | [8 empty] | NAC Plan | NAC | IAM Plan |  | SSO - Phase 0 | SSO - Phase 1 | IAM | SSO-Phase 2 |  | SSO - Phase 3 |  |  | SSO- Review
| AT | Awareness and Training | Awareness and Training | 10 |  |  |  |  | AT PS |  |  |  |  | Metrics |  |  | Orientation |  | Alignment |  |  |  | Review |  |  |  | Review
| DS | Data Security | Security Architecture and Design (Life Cycle) | 13 | - |  |  |  | CA | [7 empty] | Standards |  | Review Board | Report |  |  |  | Report |  |  |  | Report
| IP | Information Protection Processes and Procedures | Governance - Proactive Protection - - Policies, Standards, Guidelines - ITSM Process governance and maturity - Acquisition, Development and Maintenance - Application development life cycle | 11 |  |  |  |  | MP PE SA SC |  |  |  |  | Metrics (e-discovery) |  |  | Policies | Standards Baselines "Cloud" |  | MDM |  |  | IT Service Management - Automation |  |  |  | Review
| MA | Maintenance | Operations Security - Asset Maintenance | 14 | - |  |  |  | MA | [7 empty] | Asset Plan |  | Biomedical |  |  |  | Asset Management |  |  |  | Full Asset Management
| PT | Protective Technology | Operations Security - Change Management - Information Management and Encryption | 15 |  | $xxx | $xxx | $xxx | CM | [8 empty] | ITSM Review | ITSM Design | ITSM Align |  |  | Change Management |  |  |  | Review Change Mgmt.
Detect | AE | Anomalies and Events | Monitor, Alerts and Reports - SIEM-Vuln-PHI | 1b |  | $xxx | $xxx | $xxx | SI |  |  |  |  | Metrics |  |  | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test | External Pen-Test | Pen-Test | Pen-Test | Pen-Test
| CM | Security Continuous Monitoring | Monitor, Alerts and Reports | 1a | - | [11 empty] | Plan | Automation | Expand 3 |  |  |  | Expand 4 |  |  |  | Expand 5
| DP | Detection Processes | Monitor, Alerts and Reports - DLP | 1 | - | $xxx $xxx | $xxx | $xxx | [5 empty] | Metrics |  |  |  | DLP | DLP Go-Live |  | DLP Phase 2 |  | DLP Phase 3
Respond | RP | Response Planning | Governance - Business Impact Analysis | 5c | - | [8 empty] | Metrics |  |  |  |  | BIA - Phase 1 |  | BIA - Phase 2 |  | BIA - Phase 3
| CO | Communications | Incident Response - Service Alignment | 8d | - | [8 empty] | Metrics |  |  |  |  | Architecture |  | Workflow |  | Process Mapping
| AN | Analysis | Incident Response - Risk Analysis | 8a | - | $xxx | [12 empty] | Risk Mapping |  | Formal Review |  |  |  | Formal Review |  |  |  | Formal Review
| MI | Mitigation | Incident Response | 8c | - |  |  |  | IR | [9 empty] | CIRT Team |  | CIRT Test 1 |  | CIRT Full Test |  | CIRT Test 2 |  | CIRT Full Test |  | CIRT Test 3
| IM | Improvements | Incident Response - Service Maturity | 8e | - | $xxx | [10 empty] | Review | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate | External Risk Assessment | Remediate | Remediate | Remediate
Recover | RP | Recovery Planning | Operations Security - Business Continuity | 8 |  |  |  |  | CP | [9 empty] | Test BC Plan | Process Alignment | DR Plan | Formalize Update | Test BC Plan |  | Mid-year |  | Test BC Plan |  | Mid-year
| IM | Improvements | Operations Security - Downtime Management | 8b | - | [13 empty] | Document |  | Standardize Training |  | Test Downtime Plan |  |  |  | Test Downtime Plan
| CO | Communications | Operations Security - Service Alignment | 12 | - | $xxx | [7 empty] | Metrics |  |  | Major Programs | Education | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year |  | LMS Review |  | Mid-year
|  |  | Rev. 0.1 | [7 empty] | Current State |  |  | Progress Areas
|  |  | 2014-12-01 | [7 empty] | Future State |  |  | Challenge Areas